## Slide 1
An Introduction to Scrum

## Slide 2: Scrum

## Slide 3: Scrum
It is an Agile S/w development method for project management
Characteristics:
Prioritized work is done.
Completion of backlog items
Progress is explained
Agile Software Development

## Slide 4: We’re losing the relay race
Hirotaka Takeuchi and Ikujiro Nonaka, “The New New Product Development Game”, Harvard Business Review, January 1986.
“The… ‘relay race’ approach to product development…may conflict with the goals of maximum speed and flexibility. Instead a holistic or ‘rugby’ approach—where a team tries to go the distance as a unit, passing the ball back and forth—may better serve today’s competitive requirements.”
Notes: would be nice to include a quote from Wicked Problems here

## Slide 5
Scrum is an agile process that allows us to focus on delivering the highest business value in the shortest time.
It allows us to rapidly and repeatedly inspect actual working software (every two weeks to one month).
The business sets the priorities. Teams self-organize to determine the best way to deliver the highest priority features.
Every two weeks to a month anyone can see real working software and decide to release it as is or continue to enhance it for another sprint.
Scrum in 100 words

## Slide 6: What is Scrum?
Definition from rugby football:
  a scrum is a way to restart the game after an interruption, where the forwards of each side come together in a tight formation and struggle to gain possession of the ball when it is tossed in among them

## Slide 7: Scrum - an agile process
SCRUM is an agile, lightweight process for managing and controlling software and product development in rapidly changing environments.
  Iterative, incremental process
  Team-based approach
  developing systems/ products with rapidly changing requirements
  Controls the chaos of conflicting interest and needs
  Improve communication and maximize cooperation
  Protecting the team form disruptions and impediments
  A way to maximize productivity

## Slide 8: Scrum has been used by:
Microsoft
Yahoo
Google
Electronic Arts
High Moon Studios
Lockheed Martin
Philips
Siemens
Nokia
Capital One
BBC
Intuit
Intuit
Nielsen Media
First American Real Estate
BMC Software
Ipswitch
John Deere
Lexis Nexis
Sabre
Salesforce.com
Time Warner
Turner Broadcasting
Oce

## Slide 9: Scrum has been used for:
Commercial software
In-house development
Contract development
Fixed-price projects
Financial applications
ISO 9001-certified applications
Embedded systems
24x7 systems with 99.999% uptime requirements
the Joint Strike Fighter
Video game development
FDA-approved, life-critical systems
Satellite-control software
Websites
Handheld software
Mobile phones
Network switching applications
ISV applications
Some of the largest applications in use

## Slide 10: Characteristics
Self-organizing teams
Product progresses in a series of month-long “sprints”
Requirements are captured as items in a list of “product backlog”
No specific engineering practices prescribed
Uses generative rules to create an agile environment for delivering projects
One of the “agile processes”

## Slide 11: The Agile Manifesto–a statement of values
Process and tools
Individuals and interactions
over
Following a plan
Responding to change
over
Source: www.agilemanifesto.org
Comprehensive documentation
Working software
over
Contract negotiation
Customer collaboration
over

## Slide 12: Functionality of Scrum

## Slide 13: Putting it all together

## Slide 14: Sprints
Scrum projects make progress in a series of “sprints”
  Analogous to Extreme Programming iterations
Typical duration is 2–4 weeks or a calendar month at most
A constant duration leads to a better rhythm
Product is designed, coded, and tested during the sprint

## Slide 15: Sequential vs. overlapping development
Source: “The New New Product Development Game” by Takeuchi and Nonaka. Harvard Business Review, January 1986.
Rather than doing all of one thing at a time...
...Scrum teams do a little of everything all the time
Requirements
Design
Code
Test

## Slide 16: No changes during a sprint
Plan sprint durations around how long you can commit to keeping change out of the sprint
Change

## Slide 17: Scrum framework
Product owner
ScrumMaster
Team
Roles
Sprint planning
Sprint review
Sprint retrospective
Daily scrum meeting
Ceremonies
Product backlog
Sprint backlog
Burndown charts
Artifacts

## Slide 18: Scrum framework
Sprint planning
Sprint review
Sprint retrospective
Daily scrum meeting
Ceremonies
Product backlog
Sprint backlog
Burndown charts
Artifacts
Product owner
ScrumMaster
Team
Roles

## Slide 19: Product owner
Define the features of the product
Decide on release date and content
Be responsible for the profitability of the product (ROI)
Prioritize features according to market value
Adjust features and priority every iteration, as needed
Accept or reject work results
Acts like one voice (in any case)
Knows what needs to be build and in what sequence this should be done
Typically a product manager

## Slide 20: The ScrumMaster
Represents management to the project
Responsible for enacting Scrum values and practices
Removes impediments
Ensure that the team is fully functional and productive
Enable close cooperation across all roles and functions
Shield the team from external interferences
Typically filled by a Project Manager or Team Leader

## Slide 21: The scrum team
Typically 5-9 people
Cross-functional:
  Programmers, testers, user experience designers, etc.
Members should be full-time
    May be exceptions (e.g., database administrator)
Team is self-organizing
Membership can change only between sprints

## Slide 22: The team
Teams are self-organizing
  Ideally, no titles but rarely a possibility
Membership should change only between sprints

## Slide 23: Scrum framework
Product owner
ScrumMaster
Team
Roles
Product backlog
Sprint backlog
Burndown charts
Artifacts
Sprint planning
Sprint review
Sprint retrospective
Daily scrum meeting
Ceremonies

## Slide 24: Sprint Planning Meeting
A collaborative meeting in the beginning of each Sprint between the Product Owner, the Scrum Master and the Team
Takes 8 hours and consists of 2 parts (“before lunch and after lunch”)

## Slide 25: Parts of Sprint Planning Meeting
1st Part:
  Creating Product Backlog
  Determining the Sprint Goal.
  Participants: Product Owner, Scrum Master, Scrum Team
2nd Part:
  Participants: Scrum Master, Scrum Team
  Creating Sprint Backlog

## Slide 26
Sprint planning meeting
Sprint prioritization
Analyze and evaluate product backlog
Select sprint goal
Sprint planning
Decide how to achieve sprint goal (design)
Create sprint backlog (tasks) from product backlog items (user stories / features)
Estimate sprint backlog in hours
Sprint
goal
Sprint
backlog
Business conditions
Team capacity
Product backlog
Technology
Current product

## Slide 27: Sprint planning
Team selects items from the product backlog they can commit to completing
Sprint backlog is created
  Tasks are identified and each is estimated (1-16 hours)
  Collaboratively, not done alone by the ScrumMaster
High-level design is considered
As a vacation planner, I want to see photos of the hotels.
Code the middle tier (8 hours)
Code the user interface (4)
Write test fixtures (4)
Code the foo class (6)
Update performance tests (4)

## Slide 28: Pre-Project/Kickoff Meeting
A special form of Sprint Planning Meeting
Meeting before the begin of the Project

## Slide 29: Sprint
A month-long iteration, during which is incremented a product functionality
NO outside influence can interference with the Scrum team during the Sprint
Each Sprint begins with the Daily Scrum Meeting

## Slide 30: Daily Scrum
Is a short (15 minutes long) meeting, which is held every day before the Team starts working
Participants: Scrum Master (which is the chairman), Scrum Team
Every Team member should answer on 3 questions

## Slide 31: Everyone answers 3 questions
These are not status for the ScrumMaster
  They are commitments in front of peers
What did you do yesterday?
1
What will you do today?
2
Is anything in your way?
3

## Slide 32: Daily Scrum
Is NOT a problem solving session
Is NOT a way to collect information about WHO is behind the schedule
Is a meeting in which team members make commitments to each other and to the Scrum Master
Is a good way for a Scrum Master to track the progress of the Team

## Slide 33: The daily scrum
Parameters
  Daily
  15-minutes
  Stand-up
Not for problem solving
  Whole world is invited
  Only team members, ScrumMaster, product owner, can talk
Helps avoid other unnecessary meetings

## Slide 34: The sprint review
Team presents what it accomplished during the sprint
Typically takes the form of a demo of new features or underlying architecture
Informal
  2-hour prep time rule
  No slides
Whole team participates
Invite the world

## Slide 35: Sprint Review Meeting
Is held at the end of each Sprint
Business functionality which was created during the Sprint is demonstrated to the Product Owner
Informal, should not distract Team members of doing their work

## Slide 36: Sprint retrospective
Periodically take a look at what is and is not working
Typically 15–30 minutes
Done after every sprint
Whole team participates
  ScrumMaster
  Product owner
  Team
  Possibly customers and others

## Slide 37: Start / Stop / Continue
Whole team gathers and discusses what they’d like to:
Start doing
Stop doing
Continue doing
This is just one of many ways to do a sprint retrospective.

## Slide 38: Scrum framework
Product owner
ScrumMaster
Team
Roles
Sprint planning
Sprint review
Sprint retrospective
Daily scrum meeting
Ceremonies
Product backlog
Sprint backlog
Burndown charts
Artifacts

## Slide 39: Product backlog
The requirements
A list of all desired work on the project
Ideally expressed such that each item has value to the users or customers of the product
Prioritized by the product owner
Reprioritized at the start of each sprint
This is the product backlog

## Slide 40: A sample product backlog
Backlog item | Estimate
Allow a guest to make a reservation | 3
As a guest, I want to cancel a reservation. | 5
As a guest, I want to change the dates of a reservation. | 3
As a hotel employee, I can run RevPAR reports (revenue-per-available-room) | 8
Improve exception handling | 8
... | 30
... | 50

## Slide 41: Estimation of Product Backlog Items
Establishes team’s velocity (how much Effort a Team can handle in one Sprint)
Determining units of complexity.
  Size-category (“T-Shirt size”)
  Story points
  Work days/work hours
Methods of estimation:
  Expert Review
  Creating a Work Breakdown Structure (WBS)

## Slide 42: Product Backlog
Is only a FORECAST!-> is not exact

## Slide 43: Sprint Backlog
A subset of Product Backlog Items, which define the work for a Sprint
Is created ONLY by Team members
Each Item has it’s own status
Should be updated every day

## Slide 44: The sprint goal
A short statement of what the work will be focused on during the sprint
Database Application
Financial services
Life Sciences
Support features necessary for population genetics studies.
Support more technical indicators than company ABC with real-time, streaming data.
Make the application run on SQL Server in addition to Oracle.

## Slide 45: Managing the sprint backlog
Individuals sign up for work of their own choosing
  Work is never assigned
Estimated work remaining is updated daily

## Slide 46: Managing the sprint backlog
Any team member can add, delete or change the sprint backlog
Work for the sprint emerges
If work is unclear, define a sprint backlog item with a larger amount of time and break it down later
Update work remaining as more becomes known

## Slide 47: A sprint backlog
Tasks
Code the user interface
Code the middle tier
Test the middle tier
Write online help
Write the foo class
Mon
8
16
8
12
8
Tues
4
12
16
8
Wed
Thur
4
11
8
4
Fri
8
8
Add error logging
8
10
16
8
8

## Slide 48: Sprint Backlog
A subset of Product Backlog Items, which define the work for a Sprint
Is created ONLY by Team members
Each Item has it’s own status
Should be updated every day

## Slide 49: Sprint Backlog
No more then 300 tasks in the list
If a task requires more than 16 hours, it should be broken down
Team can add or subtract items from the list. Product Owner is not allowed to do it

## Slide 50: Sprint Backlog
Is a FORECAST!
Is a good warning monitor

## Slide 51: Burn down Charts
Are used to represent “work done”.
Are wonderful Information Radiators
3 Types:
  Sprint Burn down Chart (progress of the Sprint)
  Release Burn down Chart (progress of release)
  Product Burn down chart (progress of the Product)

## Slide 52: Information Radiator
"Two characteristics are key to a good information radiator. The first is that the information changes over time. This makes it worth a person's while to look at the display... The other characteristic is that it takes very little energy to view the display."

## Slide 53: Burn down Charts
X-Axis: time (usually in days)
Y-Axis: remaining effort

## Slide 54: Sprint Burn down Chart
Depicts the total Sprint Backlog hours remaining per day
Shows the estimated amount of time to release
Ideally should burn down to zero to the end of the Sprint
Actually is not a straight line
Can bump UP

## Slide 55: Release Burn down Chart
Will the release be done on right time?
X-axis: sprints
Y-axis: amount of hours remaining
The estimated work remaining can also burn up

## Slide 56: Alternative Release Burn down Chart
Consists of bars (one for each sprint)
Values on the Y-axis: positive AND negative
Is more informative then a simple chart

## Slide 57: Product Burn down Chart
Is a “big picture” view of project’s progress (all the releases)

## Slide 58: A sprint burndown chart
Hours

## Slide 59
Hours
40
30
20
10
0
Mon
Tue
Wed
Thu
Fri
Tasks
Code the user interface
Code the middle tier
Test the middle tier
Write online help
Mon
8
16
8
12
Tues
Wed
Thur
Fri
4
12
16
7
11
8
10
16
8
50

## Slide 60: Example of Sprint Burndown Chart

## Slide 61: Scalability
Typical individual team is 7 ± 2 people
  Scalability comes from teams of teams
Factors in scaling
  Type of application
  Team size
  Team dispersion
  Project duration
Scrum has been used on multiple 500+ person projects

## Slide 62: Scaling through the Scrum of scrums

## Slide 63: Scaling Scrum
A typical Scrum team is 6-10 people
Jeff Sutherland - up to over 800 people
"Scrum of Scrums" or what called "Meta-Scrum“
Frequency of meetings is based on the degree of coupling between packets

## Slide 64: Scaling Scrum

## Slide 65: Scaling Scrum

## Slide 66: Scrum of scrums of scrums

## Slide 67: Pro/Con
Advantages
  Completely developed and tested features in short iterations
  Simplicity of the process
  Clearly defined rules
  Increasing productivity
  Self-organizing
  each team member carries a lot of responsibility
  Improved communication
  Combination with Extreme Programming
Drawbacks
  “Undisciplined hacking” (no written documentation)
  Violation of responsibility
  Current mainly carried by the inventors

## Slide 68
www.mountaingoatsoftware.com